## Vision
PRODUCT VISION
Triple-I RecallFeed is a web based application designed to provide consumers with FDA enforcement report for Food Recall. It further allows consumers to search by 'Food Name', Date Range and Seriousness of Recall. It is powered by openFDA dataset for food recalls and uses wide range of open-source technologies. The applicaiton will be developed following steps outlines in U.S. Digital Services Playbook and an agile iterative methodology will be used in developing the applicaiton. A human-centered design technique and tools will be used to design the application Development will use test drive development, unit testing with continuous integration, build and deploy using open-source, no licensing and free of cost technologies The applicaiton will be deployed and hosted on a public Platform (IaaS or Paas)

## Roadmap
6/19/2015 - 7/07/15
RecallsFeed Roadmap
| 2015-06-19 | 2015-06-22 | 2015-06-23 | 2015-06-24 | 2015-06-25 | 2015-06-26 | 2015-06-29 | 2015-06-30 | 2015-07-01 | 2015-07-02 | 2015-07-06 | 2015-07-07
Assign one leader for prototype | bar: 2015-06-19
Assemble multi-disciplinary and collaborative team including a minimum of 5 Labor categories | bar: 2015-06-19
Identify users to be used in the prototype design and development process | bar: 2015-06-19
Using 3 "human-centered Design" tools come up with initial wireframes | bar: 2015-06-19 to 2015-06-22
Perform Usability Test on people - paper | bar: 2015-06-23
Perform Usability Test on people - template | bar: 2015-06-24
Perform Usability Test on people - application | bar: 2015-06-30 to 2015-07-01
used an iterative approach, where feedback informed subsequent work of the prototype | bar: 2015-06-23 to 2015-07-02
Create html templates using design style sheets and pattern library | bar: 2015-06-23
Develop the prototype using 5 open-source technologies (develop, write unit test, test, review, incorporate feedback) - multiple device & responsive support. | bar: 2015-06-24 to 2015-07-07
Setup Continuous Integration /automate the running of tests/ & continuously deploy code to PaaS provider | bar: 2015-06-24
Setup Configuration Management | bar: 2015-06-25
Deploy Software in a container (Docker) | bar: 2015-06-26
Setup Continuous Monitoring | bar: 2015-07-01 to 2015-07-02
Provide documentation to install and run prototype on another machine | bar: 2015-07-06

## Team
RecallsFeed TEAM COMPOSITION
Product Manager | Person A
Frontend Developer | Person B
Backend Developer | Person C
Technical Architect | Person D
Visual Designer | Person E
DevOps Engineer | Person F
Usability Engineer | Person G

## Release
RecallsFeed RELEASE | 6/19/2015 - 7/07/15
RecallFeed Roadmap
| 2015-06-19 | 2015-06-22 | 2015-06-23 | 2015-06-24 | 2015-06-25 | 2015-06-26 | 2015-06-29 | 2015-06-30 | 2015-07-01 | 2015-07-02 | 2015-07-06 | 2015-07-07
1st working copy of beta prototype for users | bar: 2015-06-26
2nd working copy of beta prototpye for users | 2015-06-29: 2
3rd working copy of beta prototype for users | 2015-06-30: 3
4th working copy of beta prototype for users | 2015-07-01: 4
5th working copy of beta prototype for users | 2015-07-02: 5
1st Release v1.0.0 of prototype | 2015-07-06: 6
2nd Release v2.0.0 of prototype | 2015-07-07: 7

## User Stories
USER STORIES
USER STORY #1 | A worried mother just heard on TV traces of peanut were found in food packages, she would like to find out more details of the recall from official source
USER STORY #2 | A house wife has heard about lot of food recalls on TV and facebook, would like to check if any of the food in her pantry is on the list of recall'd food
USER STORY #3 | A school cafeteria manager would like to access the latest food recall list, print the list on a weekly basis and share it with cafeteria staff on a weekly basis

## Feature Backlog
SPRINT | ACTIVITIES | 6/19/2015 - 7/07/15
SPRINT 0 |  | 2015-06-19 | 2015-06-22 | 2015-06-23 | 2015-06-24 | 2015-06-25 | 2015-06-26 | 2015-06-29 | 2015-06-30 | 2015-07-01 | 2015-07-02 | 2015-07-06 | 2015-07-07
Sprint-0 | Get the Team created
Sprint-0 | Setup necessary access for the team on GitHub
Sprint-0 | Setup the necessary development environment for development of code and access to tools needed.
SPRINT 1
Sprint 1 Planning | Sprint Planning Meeting (A short meeting) - All team members get together and agree on Goal - Every team member exactly know what to achieve in the sprint
Sprint-1 | Setup the DevOps environment for - continuous integration, build and deploy - Configuration Maangement - Configure continuous monitoring
Sprint-1 | Deploy Docker Image via Docker Hub
Sprint-1 | Using human-centered design approach, create the PERSONA, SCENARIO and USE-CASES
Sprint-1 | Using the persona, scenario, use-cases and input from users create the initial wireframes
Sprint-1 | Iteratively evolve the wireframes getting feedback from users
Sprint-1 | Conduct paper-based Usability testing on evolved wireframe
Sprint-1 | Incorporate suggestion/feedback from the paper-based usability testing into wireframes
Sprint-1 | Develop HTML templates from the evolved wireframes
Sprint-1 | Conduct Usability testing on html templates
Sprint-1 | Incorporate changes to templates with feedback from Usability testing
Sprint-1 | Develop prototype application using the latest html templates, using TDD and continuous integration/deployment environment setup
Sprint-1 | Review and test prototype after every nightly build, going through feedback/suggestion. With agreement of product manager add it to Task list for engineers to take care
Sprint-1 | Conduct the final usability testing on working copy of prototype, document and provide feedback via the daily scrum meeting

## Bug & Task Backlog
No | Problems | Type | Product Owner | Team | Comments
1 | Carousel not rotated | Functional Testing | Y | Y
2 | Clicking the Carousel should take me to detail recall on that product | Usability Testing | Y | Y
3 | Food Name & Date combine search gets out of date range records | Functional Testing | Y | Y
4 | Introduce borders around event detail page. | Functional Testing | Y | Y
5 | Mobile phone (Samsung 5.0"), the recall date is not showing | Functional Testing | Y | Y
6 | Mobile phone (Samsung 5.0" android), the date picker has erroneous data loaded | Functional Testing | Y | Y
7 | Show image of recall product | Usability Testing | N (for prototype)
8 | Allow users iterate to next 100 records | Functional Testing | N (for prototype)
9 | Add help to Seriousness label, not everyone knows what it is | Usability Testing | Y | Y
10 | Add focus to SEARCH box, with focus users during usability testing did not notice it. | Usability Testing | Y | Y
11 | Enhance the message to display Food Name and Seriousness, in addition to date range. | Functional Testing | Y | Y
12 | Change "Filter Datasets" label for table search to say "Filter search results with keywords" | Usability Testing | Y | Y
13 | Provide a disclaimer on the website, not official FDA | Functional Testing | Y | Y
14 | Recall or Report date is important to know when food recall happened | Usability Testing | Y | Y
15 | Can we search by exact food name | Usability Testing | N (for prototype) |  | Current dataset does not provide exact food name's. Food names can be searched in recall description
16 | Indica Food Name field is optional during search | Functional Testing | Y | Y
NB